## GanttChart
PROJECT TITLE |  | Community Garden
PROJECT MANAGER |  | King Sambonge
WBS NUMBER | TASK TITLE | Dependencies (WBS #) | START DATE | DUE DATE | DURATION | % OF TASK COMPLETE | PAHSE 1 | [14 empty] | PHASE 2 | [14 empty] | PHASE 3 | [14 empty] | PHASE 4
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
1.1 | Phase: Planning & Approval |  |  | -1
1.1.1 | Form steering committee |  | 2026-06-01 | 2026-06-05 | 5 | 100% | bar: WEEK 1 M to WEEK 1 F; WEEK 5 W to WEEK 5 F
1.1.2 | Draft project proposal | 1.1.1 | 2026-06-08 | 2026-06-12 | 5 | 100% | bar: WEEK 5 W to WEEK 5 F
1.1.3 | Secure approval from Parks Dept. | 1.1.2 | 2026-06-15 | 2026-06-29 | 15 | 100% | bar: WEEK 3 M to WEEK 5 F
1.1.4 | Obtain necessary permits | 1.1.3 | 2026-07-06 | 2026-07-15 | 10 | 100% | bar: WEEK 2 M to WEEK 3 F; WEEK 5 W to WEEK 5 F
1.1.5 | Host community input & design meeting | 1.1.3 | 2026-07-06 | 2026-07-06 | 1 | 100% | bar: WEEK 2 M; WEEK 5 W to WEEK 5 F
1.1.6 | Create final garden layout & plot map | 1.1.5 | 2026-07-07 | 2026-07-11 | 5 | 100% | bar: WEEK 2 T to WEEK 3 M; WEEK 5 W to WEEK 5 F
1.1.7 | Create resource garden layout & get supplier quotes | 1.1.6 | 2026-07-14 | 2026-07-23 | 10 | 100% | bar: WEEK 3 T to WEEK 5 M; WEEK 5 W to WEEK 5 F
1.2 | Phase: Site Preparation & Procurement |  |  | -1
1.2.1 | Test soil & clear site | 1.1.4 | 2026-07-20 | 2026-07-24 | 5 | 100% | bar: WEEK 4 M to WEEK 4 F; WEEK 5 W to WEEK 5 F
1.2.2 | Mark out layout with stakes | 1.2.1 & 1.1.6 | 2026-07-27 | 2026-07-28 | 2 | 100%
1.2.3 | Order & procure all bulk materials | 1.1.7 | 2026-07-28 | 2026-08-01 | 5 | 100% | bar: WEEK 5 W to WEEK 6 T
1.2.4 | Purchase tools, shed & irrigation | 1.1.7 | 2026-07-28 | 2026-08-01 | 5 | 100% | bar: WEEK 5 W to WEEK 6 T
1.3 | Phase: Construction & Build-Out |  |  | -1
1.3.1 | Assemble & place raised beds | 1.2.2 & 1.2.3 | 2026-08-04 | 2026-08-06 | 3 | 40% | bar: WEEK 5 W to WEEK 5 F; WEEK 7 T to WEEK 7 TH
1.3.2 | Fill beds with soil and compost | 1.3.1 | 2026-08-07 | 2026-08-08 | 2 | bar: WEEK 5 W to WEEK 5 F; WEEK 7 F to WEEK 8 M
1.3.3 | Install irrigation & water access | 1.2.2 & 1.2.4 | 2026-08-04 | 2026-08-06 | 3 | 60% | bar: WEEK 5 W to WEEK 5 F; WEEK 7 T to WEEK 7 TH
1.3.4 | Lay walkways & install fencing | 1.2.2 & 1.2.3 | 2026-08-04 | 2026-08-07 | 4 | 80% | bar: WEEK 5 W to WEEK 5 F; WEEK 7 T to WEEK 7 F
1.3.5 | Assemble tool shed | 1.2.4 | 2026-08-04 | 2026-08-04 | 1 | 60% | bar: WEEK 5 W to WEEK 5 F; WEEK 7 T
1.3.6 | Build community areas (bins, benches) | 1.2.3 & 1.2.4 | 2026-08-05 | 2026-08-06 | 2 | 40% | bar: WEEK 5 W to WEEK 5 F; WEEK 7 W to WEEK 7 TH
1.4 | Phase: Launch & Handover |  |  | -1
1.4.1 | Manage plot registration & assignment | 1.3.2 | 2026-08-11 | 2026-08-20 | 10 | bar: WEEK 5 W to WEEK 5 F; WEEK 10 T to WEEK 12 M
1.4.2 | Host "Garden Orientation" day | 1.4.1 | 2026-08-25 | 2026-08-25 | 1 | bar: WEEK 5 W to WEEK 5 F; WEEK 11 T
1.4.3 | Plan & host Grand Opening event | 1.4.2 | 2026-08-26 | 2026-08-30 | 5 | bar: WEEK 5 W to WEEK 5 F; WEEK 11 W to WEEK 12 T
1.4.4 | Finalize & handover project documents | 1.4.2 | 2026-08-26 | 2026-08-28 | 3 | bar: WEEK 5 W to WEEK 5 F; WEEK 11 W to WEEK 11 F