## KanbanBoard
Backlog (All Remaining Tasks) | To Do (This Week's Build) | In Progress (Actively Working) | On Hold / Blocked | Done (Completed Tasks)
1.3.2 Fill beds with soil | 1.3.1 Assemble & place raised beds | 1.3.3 Install irrigation & water access | 1.3.4 Lay walkways & install fencing (Blocked: Fencing delivery delayed) | 1.1.1 Form steering committee
1.4.1 Manage plot registration | 1.3.6 Build community areas | 1.3.5 Assemble tool shed |  | 1.1.2 Draft project proposal
1.4.2 Host "Garden Orientation" |  |  |  | 1.1.3 Secure approval
1.4.3 Plan & host Grand Opening |  |  |  | 1.1.4 Obtain necessary permits
1.4.4 Finalize & handover documents |  |  |  | 1.1.5 Host community meeting
1.1.6 Create final garden layout
1.1.7 Create resource plan
1.2.1 Test soil & clear site
1.2.2 Mark out layout
1.2.3 Order all bulk materials
1.2.4 Purchase tools, shed & irrigation