## WBS
WBS # | Phase | Task Name
1 | Project | Community Garden (3-Month Build)
1.1 | Planning & Approval | Phase 1 Total
1.1.1 | Planning & Approval | Form steering committee
1.1.2 | Planning & Approval | Draft project proposal
1.1.3 | Planning & Approval | Secure approval from Parks Dept.
1.1.4 | Planning & Approval | Obtain necessary permits
1.1.5 | Planning & Approval | Host community input & design meeting
1.1.6 | Planning & Approval | Create final garden layout & plot map
1.1.7 | Planning & Approval | Create resource plan & get supplier quotes
1.2 | Site Prep & Procurement | Phase 2 Total
1.2.1 | Site Prep & Procurement | Test soil & clear site
1.2.2 | Site Prep & Procurement | Mark out layout with stakes
1.2.3 | Site Prep & Procurement | Order & procure all bulk materials
1.2.4 | Site Prep & Procurement | Purchase tools, shed & irrigation
1.3 | Construction & Build-Out | Phase 3 Total
1.3.1 | Construction & Build-Out | Assemble & place raised beds
1.3.2 | Construction & Build-Out | Fill beds with soil and compost
1.3.3 | Construction & Build-Out | Install irrigation & water access
1.3.4 | Construction & Build-Out | Lay walkways & install fencing
1.3.5 | Construction & Build-Out | Assemble tool shed
1.3.6 | Construction & Build-Out | Build community areas (bins, benches)
1.4 | Launch & Handover | Phase 4 Total
1.4.1 | Launch & Handover | Manage plot registration & assignment
1.4.2 | Launch & Handover | Host "Garden Orientation" day
1.4.3 | Launch & Handover | Plan & host Grand Opening event
1.4.4 | Launch & Handover | Finalize & handover project documents